## Sheet1
Phase | Start Date | End Date | Duration (Days) | Milestone
Project Preparation | 2025-01-27 | 2025-03-14 | 47 | Completion of project preparation
Data Preparation & Initial Prototyping | 2025-03-15 | 2025-04-20 | 37
Implementation & Optimization | 2025-04-21 | 2025-05-16 | 26 | Project Preparation Presentation Slides completed
Refinement & Comparative Analysis | 2025-05-17 | 2025-07-05 | 50 | Comparative analysis completed
Finalization & Dissertation Writing | 2025-07-06 | 2025-08-10 | 36 | Final dissertation submission